## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 作业检查 | 作为一个工作繁忙并且水平不是很高的家长，我希望能够进行作业检查，以便于减轻我人工检查孩子英语作业的负担。 | initial | not D | 3 | 4 |  |  | 3
2 | 1 | 1 | user story | 作业情况评估 | 作为一个家长，我希望检查完孩子作业对错后能对孩子的本次作业完成情况有一个整体的评估，以便于我快速直观了解孩子的学习情况。 | initial | not D | 1 | 1 |  |  | 1
3 | 1 | 1 | user story | 错题类型显示 | 作为一个学生家长，我希望有一个错题类型的显示，以便于学生知道哪个知识点薄弱，及时巩固 | initial | not D | 1 | 1 |  |  | 1
4 | 1 | 1 | user story | 查看正确答案 | 作为一个学生家长，我希望有一个正确答案提醒，以便于学生改正后查看是否正确 | initial | not D | 1 | 1 |  |  | 1
5 | 1 | 1 | user story | 作业解答 | 作为一个学生，希望有作业的讲解 | initial | not D | 1 | 4 |  |  | 1
6 | 1 | 1 | user story | 习题推荐 | 作为一个学生，希望针对错题有类似问题的推荐 | initial | not D | 2 | 4 |  |  | 2
7 | 1 | 1 | user story | 搜索习题 | 作为老师，希望可以搜索各种类型的习题 | initial | not D | 2 | 2 |  |  | 2
8 | 1 | 1 | user story | 提交标准答案并保存 | 作为批改作业的老师，希望可以将正确答案或判断标准通过拍照或者电脑输入的方式上传并保存 | initial | not D | 2 | 2 |  |  | 2
9 | 1 | 1 | user story | 生成习题 | 作为一个学习出色的同学，我希望有一个生成习题的功能，以便于我能更好的巩固学业 | initial | not D | 1 | 3 |  |  | 1
10 | 1 | 1 | user story | 拍照或图片上传 | 作为学生，希望既可以拍照上传也可以选择图片上传 | initial | not D | 1 | 1 |  |  | 1
11 | 1 | 1 | user story | 登录方式 | 作为注册用户，希望采取便捷的QQ关联授权直接登录 | initial | not D | 1 | 1 |  |  | 1
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information